## 📋 Cover
RAID LOG
Risks · Assumptions · Issues · Dependencies
| Programme Name | [PROGRAMME NAME]
| Programme Manager | Anushree Nair
| Reporting Period | [START DATE] – [END DATE]
| Version | v1.0
| Last Updated | [DATE]
| Status | [ACTIVE / CLOSED]
About This Log
This RAID Log is a living governance document. Update it weekly as part of your programme rhythm.
Each tab covers one RAID category. Use the colour-coded RAG status to surface issues quickly.
Escalate items rated HIGH or CRITICAL to your Steering Committee without delay.
Tabs in This Workbook
| 🔴 Risks | Track threats to programme delivery with likelihood & impact scoring
| 🟡 Assumptions | Log key assumptions underpinning plans and validate them over time
| 🟠 Issues | Record live problems affecting delivery, owners and resolution dates
| 🔵 Dependencies | Map internal and external dependencies critical to programme success
Created by Anushree Nair ¦ Programme Manager ¦ linkedin.com/in/anushree-nair
⚠️ If you use or adapt this template, please credit Anushree Nair and reach out on LinkedIn.

## 🔴 Risks
RISKS
Risk ID | Date Raised | Raised By | Workstream | Risk Description | Category | Likelihood (1-5) | Impact (1-5) | Risk Score (L×I) | Risk Rating | RAG Status | Mitigation Action | Owner | Target Date | Status | Review Date | Notes
R-001 | 2025-01-10 | Anushree Nair | AI Delivery | Third-party AI model vendor may not meet SLA commitments | Vendor / External | 4 | 4 |  | HIGH | AMBER | Initiate SLA review and identify backup vendor. Escalate to SteerCo if unresolved by Q1 end. | [Owner Name] | 2025-02-01 | Open | 2025-01-24 | Vendor under review
R-002 | 2025-01-12 | [Name] | Data | Key data migration resource has single point of failure — only one SME available | Resource | 3 | 5 |  | HIGH | RED | Cross-train second resource immediately. Add to sprint backlog. | [Owner Name] | 2025-01-20 | In Progress | 2025-01-24 | Escalated to Programme Board
R-003 | 2025-01-15 | [Name] | Integration | API integration with legacy system may cause delays if documentation is incomplete | Technical | 3 | 3 |  | MEDIUM | AMBER | Request full API documentation from legacy team. Schedule technical spike. | [Owner Name] | 2025-02-10 | Open | 2025-01-24
Created by Anushree Nair ¦ Programme Manager ¦ linkedin.com/in/anushree-nair ¦ ⚠️ Please credit the author if you use or adapt this template.

## 🟡 Assumptions
ASSUMPTIONS
Assumption ID | Date Raised | Raised By | Workstream | Assumption Description | Basis / Rationale | Impact if Wrong | Likelihood of Being Wrong | Owner | Validation Method | Validation Date | Status | RAG Status | Notes
A-001 | 2025-01-10 | Anushree Nair | Programme | Business stakeholders will be available for sprint reviews every two weeks | Agreed in programme kick-off | Sprint feedback cycles break down, rework increases | LOW | [Owner Name] | Attendance confirmed in kick-off minutes | 2025-01-10 | Valid | GREEN | Confirmed in minutes
A-002 | 2025-01-12 | [Name] | AI Delivery | AI model training data will be available and clean by Sprint 3 | Data team committed verbally | Model training delayed by 4–6 weeks | MEDIUM | [Owner Name] | Validate with data team in Sprint 1 review | 2025-02-01 | Under Review | AMBER | Data audit underway
A-003 | 2025-01-15 | [Name] | Integration | Legacy system will support REST API integration without middleware | Initial technical assessment | Major re-architecture required — 8+ week delay | HIGH | [Owner Name] | Technical spike in Sprint 2 | 2025-02-14 | At Risk | RED | Spike results pending
Created by Anushree Nair ¦ Programme Manager ¦ linkedin.com/in/anushree-nair ¦ ⚠️ Please credit the author if you use or adapt this template.

## 🟠 Issues
ISSUES
Issue ID | Date Raised | Raised By | Workstream | Issue Description | Impact Description | Priority | RAG Status | Owner | Resolution Action | Target Resolution Date | Actual Resolution Date | Status | Escalated? | Escalated To | Notes
I-001 | 2025-01-11 | Anushree Nair | Data | Data pipeline failure causing daily report delays of 3+ hours | Executive dashboard not updated — SteerCo reporting at risk | HIGH | RED | [Owner Name] | Immediate fix deployed to pipeline. Root cause analysis scheduled. | 2025-01-18 |  | In Progress | Yes | Programme Director | RCA scheduled 2025-01-20
I-002 | 2025-01-14 | [Name] | Delivery | Sprint velocity dropped 30% due to unplanned BAU work pulled from team | Two sprint goals at risk — delivery timeline may slip | HIGH | AMBER | [Owner Name] | Shield team from BAU via agreement with line manager. Add buffer to plan. | 2025-01-28 |  | Open | No |  | Line manager conversation needed
I-003 | 2025-01-16 | [Name] | Governance | Steering Committee quorum not met — key decisions deferred two weeks | Programme decisions blocked, increasing downstream risk | MEDIUM | AMBER | [Owner Name] | Re-schedule SteerCo with mandatory attendance policy. Delegate sign-off where possible. | 2025-01-30 |  | Open | No
Created by Anushree Nair ¦ Programme Manager ¦ linkedin.com/in/anushree-nair ¦ ⚠️ Please credit the author if you use or adapt this template.

## 🔵 Dependencies
DEPENDENCIES
Dependency ID | Date Raised | Raised By | Workstream | Dependency Description | Type | Depends On (Team/System) | Required By Date | Priority | RAG Status | Owner | Action Required | Status | Risk if Unmet | Notes
D-001 | 2025-01-10 | Anushree Nair | AI Delivery | AI model deployment requires cloud infrastructure provisioned by Platform team | Internal | Platform Engineering | 2025-02-01 | HIGH | AMBER | [Owner Name] | Raise infrastructure request. Track weekly with Platform lead. | In Progress | Model deployment delayed — sprint goal at risk | Request raised 2025-01-10
D-002 | 2025-01-13 | [Name] | Integration | User acceptance testing requires sign-off from Legal on data privacy impact assessment | External / Compliance | Legal & Compliance | 2025-02-15 | HIGH | RED | [Owner Name] | Escalate to Legal Head. Provide DPIA draft by 2025-01-20. | Blocked | UAT cannot proceed — programme milestone at risk | Escalated to Programme Director
D-003 | 2025-01-15 | [Name] | Reporting | Sprint reporting dashboard requires data feed from Finance system | Internal | Finance Systems | 2025-02-28 | MEDIUM | GREEN | [Owner Name] | Finance team confirmed feed in scope. Monitor delivery. | On Track | Reporting delayed if feed not delivered | Confirmed in writing
Created by Anushree Nair ¦ Programme Manager ¦ linkedin.com/in/anushree-nair ¦ ⚠️ Please credit the author if you use or adapt this template.