## 📋 Cover
SPRINT REPORTING DASHBOARD
Programme Health · Sprint Metrics · Velocity · RAG Status
| Programme Name | [PROGRAMME NAME]
| Programme Manager | Anushree Nair
| Reporting Period | [START DATE] – [END DATE]
| Current Sprint | [SPRINT NUMBER]
| Total Sprints | [TOTAL NUMBER OF SPRINTS]
| Sprint Length | [1 / 2 / 3 weeks]
| Version | v1.0
| Last Updated | [DATE]
Tabs in This Workbook
| 📊 Programme Health | Overall RAG status, key metrics and programme summary
| 🏃 Sprint Log | Sprint-by-sprint tracking — velocity, goals, RAG status
| 📈 Velocity Chart | Visual velocity trend across all sprints
| ⚠️ Risks & Issues | Active risks and issues impacting sprint delivery
| ✅ Decisions Log | Key decisions made during the programme
Created by Anushree Nair ¦ Programme Manager ¦ linkedin.com/in/anushree-nair
⚠️ If you use or adapt this template, please credit Anushree Nair and reach out on LinkedIn.

## 📊 Programme Health
PROGRAMME HEALTH DASHBOARD
Programme: [PROGRAMME NAME] ¦ Manager: Anushree Nair ¦ Reporting Period: [DATE]
Overall Programme RAG Status
Overall Status | Schedule | Budget | Resources | Risks | Scope
AMBER | AMBER | GREEN | GREEN | RED | GREEN
Key Programme Metrics
Metric | Target | Actual | Variance | RAG | Notes
Sprints Completed | [TOTAL] | [ACTUAL] |  | GREEN | On track
Story Points Planned | [TARGET] | [ACTUAL] |  | AMBER | Slight underdelivery Sprint 3
Story Points Delivered | [TARGET] | [ACTUAL] |  | AMBER | Velocity stabilising
Average Velocity | [TARGET] | [ACTUAL] |  | GREEN | Improving trend
Scope Changes | 0 | [ACTUAL] |  | AMBER | 2 approved change requests
Open Risks (High+) | 0 | [ACTUAL] |  | RED | 3 high risks require action
Open Issues | 0 | [ACTUAL] |  | AMBER | 2 issues in progress
Budget Utilisation (%) | 100% | [ACTUAL] |  | GREEN | Within tolerance
Programme Summary & Commentary
Highlights | [What went well this period? Key achievements and milestones reached.]
Concerns | [What is at risk? What issues need attention from leadership?]
Decisions Required | [What decisions are needed from SteerCo or Programme Director this period?]
Next Period Focus | [What are the priorities and key activities for the next reporting period?]
Created by Anushree Nair ¦ Programme Manager ¦ linkedin.com/in/anushree-nair ¦ ⚠️ Please credit the author if you use or adapt this template.

## 🏃 Sprint Log
SPRINT LOG
Sprint # | Sprint Name | Start Date | End Date | Sprint Goal | Team / Workstream | Points Planned | Points Delivered | Completion % | Velocity | RAG Status | Goal Met? | Key Achievements | Blockers / Issues | Carry-Over Items | Notes
S01 | Sprint 1 — Foundation | 2025-01-06 | 2025-01-17 | Establish core data pipeline and baseline architecture | Data & Platform | 40 | 38 |  | 38 | GREEN | Yes | Core pipeline live. Architecture signed off. Team onboarded. | Minor environment setup delays — resolved by day 3. | 2 UI stories moved to S02 | Strong start — team gelled well
S02 | Sprint 2 — Integration | 2025-01-20 | 2025-01-31 | Integrate legacy system API and validate data flow end-to-end | Integration | 45 | 40 |  | 40 | AMBER | Partial | API integration 80% complete. Data validation passing. | Legacy API documentation incomplete — technical spike needed. | 3 integration stories carried over | Spike added to S03 backlog
S03 | Sprint 3 — AI Model v1 | 2025-02-03 | 2025-02-14 | Train and validate first AI model iteration on clean dataset | AI Delivery | 50 | 35 |  | 35 | RED | No | Model training complete. Initial accuracy below threshold. | Data quality issues identified — 20% of dataset unusable. | Model retraining in S04 | Data remediation underway — escalated to Data Lead
S04 | Sprint 4 — Remediation | 2025-02-17 | 2025-02-28 | Remediate data quality issues and retrain AI model to target accuracy | AI Delivery & Data | 48 | 48 |  | 48 | GREEN | Yes | Data remediated. Model retrained — accuracy now above threshold. | None significant. |  | Velocity recovered — team confidence high
S05 | Sprint 5 — UAT Prep | 2025-03-03 | 2025-03-14 | Prepare UAT environment, test scripts and business user onboarding | QA & Business | 42 | 40 |  | 40 | AMBER | Partial | UAT environment live. 80% of test scripts complete. | Legal sign-off on DPIA delayed — UAT start pushed 1 week. | Remaining test scripts to S06 | Escalated to Legal Head
TOTALS / AVERAGES
Created by Anushree Nair ¦ Programme Manager ¦ linkedin.com/in/anushree-nair ¦ ⚠️ Please credit the author if you use or adapt this template.

## 📈 Velocity Chart
SPRINT VELOCITY TRACKER
Sprint | Points Planned | Points Delivered | Velocity
Sprint 1 | 40 | 38 | 38
Sprint 2 | 45 | 40 | 40
Sprint 3 | 50 | 35 | 35
Sprint 4 | 48 | 48 | 48
Sprint 5 | 42 | 40 | 40
Sprint 6 | [PLANNED] | [ACTUAL] | [VELOCITY]
Sprint 7 | [PLANNED] | [ACTUAL] | [VELOCITY]
Sprint 8 | [PLANNED] | [ACTUAL] | [VELOCITY]
Metric | Value
Total Points Planned
Total Points Delivered
Overall Completion %
Average Velocity
Highest Velocity Sprint
Lowest Velocity Sprint
Created by Anushree Nair ¦ Programme Manager ¦ linkedin.com/in/anushree-nair ¦ ⚠️ Please credit the author if you use or adapt this template.

## ⚠️ Risks & Issues
SPRINT-LEVEL RISKS & ISSUES
ID | Type | Sprint | Description | Impact | Priority | RAG | Owner | Action | Due Date | Status
R-001 | Risk | S02 | Legacy API documentation incomplete — integration at risk | Sprint 2 goal partially missed — 3 stories carried over | HIGH | AMBER | [Tech Lead] | Technical spike scheduled Sprint 3. Request docs from legacy team. | 2025-01-31 | In Progress
R-002 | Risk | S03 | Data quality issues — 20% dataset unusable for AI model | Model accuracy below threshold — retraining required | HIGH | RED | [Data Lead] | Data remediation plan in place. Completed Sprint 4. | 2025-02-14 | Resolved
I-001 | Issue | S05 | Legal DPIA sign-off delayed — UAT start pushed 1 week | UAT milestone at risk — programme timeline impact | HIGH | AMBER | [PM] | Escalated to Legal Head. Interim sign-off being explored. | 2025-03-07 | In Progress
I-002 | Issue | S03 | Team velocity dropped 30% due to data rework | Sprint 3 goal not met — AI model delivery delayed | MEDIUM | AMBER | [Workstream Lead] | Shield team from unplanned work. Velocity recovered S04. | 2025-02-14 | Resolved
Created by Anushree Nair ¦ Programme Manager ¦ linkedin.com/in/anushree-nair ¦ ⚠️ Please credit the author if you use or adapt this template.

## ✅ Decisions Log
DECISIONS LOG
Decision ID | Date | Sprint | Decision Made | Rationale | Made By | Impact | Status | Notes
D-001 | 2025-01-08 | S01 | Adopt 2-week sprint cadence for all workstreams | Balances delivery pace with governance overhead for medium programme | Programme Manager | Consistent delivery rhythm — all teams aligned | Approved | Agreed at kick-off
D-002 | 2025-01-20 | S02 | Conduct technical spike on legacy API in Sprint 3 | Incomplete documentation makes integration estimation unreliable | Technical Lead | Sprint 3 capacity reduced by 20% for spike | Approved | Spike time-boxed to 3 days
D-003 | 2025-02-05 | S03 | Escalate data quality issue to Programme Director | 20% data unusable — beyond PM authority to resolve alone | Programme Manager | Data remediation plan commissioned — Sprint 4 replan | Approved | Director engaged — remediation funded
D-004 | 2025-02-17 | S04 | Replan Sprint 5 to include UAT preparation | Model now stable — earlier UAT prep reduces downstream risk | Programme Manager | Sprint 5 scope adjusted — team capacity reallocated | Approved | Product Owner signed off revised backlog
Created by Anushree Nair ¦ Programme Manager ¦ linkedin.com/in/anushree-nair ¦ ⚠️ Please credit the author if you use or adapt this template.